## Sheet1
Building_Name | S.No. | Particulars | Unit (₹/%) | By the end of Last Quarter | By the end of Current Quarter | docs | Extracted_PDF_Amount | Verification_Status
| 1 | Total Estimated cost of the Internal and External Development Works including amenities and Facilities | ₹ | 60,00,000.00 | 60,00,000.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/9f714dd0-178f-400a-a88e-5d7f4c3d0e08.pdf | 6000000 | Match
| 2 | Cost incurred against the estimated cost | ₹ | 21,30,000.00 | 36,45,836.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/9f714dd0-178f-400a-a88e-5d7f4c3d0e08.pdf | 3645836 | Match
| 3 | Work done in Percentage (as Percentage of the estimated Cost) | % | 36.00 | 61.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/9f714dd0-178f-400a-a88e-5d7f4c3d0e08.pdf | 80 | Mismatch
| 4 | Balanced Cost to be Incurred (Based on Estimated Cost) | ₹ | 38,70,000.00 | 23,54,164.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/9f714dd0-178f-400a-a88e-5d7f4c3d0e08.pdf | 2354164 | Match
| 5 | Cost Incurred on Additional/Extra Items not included in the Estimated Cost | ₹ | 0.00 | 0.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/9f714dd0-178f-400a-a88e-5d7f4c3d0e08.pdf | 0 | Match