## Sheet1
Building_Name | S.No. | Particulars | Unit (₹/%) | By the end of Last Quarter | By the end of Current Quarter | docs | Extracted_PDF_Amount | Verification_Status
| 1 | Total Estimated cost of the Internal and External Development Works including amenities and Facilities | ₹ | 30,00,000.00 | 30,00,000.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/0d684d0a-ffbe-416b-b67b-3a657b974b8f.pdf | 3000000 | Match
| 2 | Cost incurred against the estimated cost | ₹ | 19,80,000.00 | 19,80,000.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/0d684d0a-ffbe-416b-b67b-3a657b974b8f.pdf | 980000 | Mismatch
| 3 | Work done in Percentage (as Percentage of the estimated Cost) | % | 66.00 | 66.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/0d684d0a-ffbe-416b-b67b-3a657b974b8f.pdf | 66 | Match
| 4 | Balanced Cost to be Incurred (Based on Estimated Cost) | ₹ | 10,20,000.00 | 10,20,000.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/0d684d0a-ffbe-416b-b67b-3a657b974b8f.pdf | 1020000 | Match
| 5 | Cost Incurred on Additional/Extra Items not included in the Estimated Cost | ₹ | 0.00 | 0.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/0d684d0a-ffbe-416b-b67b-3a657b974b8f.pdf | 0 | Match