## Table A
Building_Name | S.No. | Particulars | Unit (₹/%) | By the end of Last Quarter | By the end of Current Quarter | docs
N/A | 1 | Total Estimated cost of the Internal and External Development Works including amenities and Facilities | ₹ | 3,77,73,000.00 | 3,77,73,000.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/08514f69-7d89-4922-9f81-df80eaf171d2.pdf
N/A | 2 | Cost incurred against the estimated cost | ₹ | 1,92,25,280.00 | 2,02,03,960.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/08514f69-7d89-4922-9f81-df80eaf171d2.pdf
N/A | 3 | Work done in Percentage (as Percentage of the estimated Cost) | % | 51.00 | 53.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/08514f69-7d89-4922-9f81-df80eaf171d2.pdf
N/A | 4 | Balanced Cost to be Incurred (Based on Estimated Cost) | ₹ | 1,85,47,720.00 | 1,75,69,040.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/08514f69-7d89-4922-9f81-df80eaf171d2.pdf
N/A | 5 | Cost Incurred on Additional/Extra Items not included in the Estimated Cost | ₹ | 0.00 | 0.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/08514f69-7d89-4922-9f81-df80eaf171d2.pdf