## Sheet1
Building_Name | S.No. | Particulars | Unit (₹/%) | By the end of Last Quarter | By the end of Current Quarter | docs | Extracted_PDF_Amount | Verification_Status
| 1 | Total Estimated cost of the Internal and External Development Works including amenities and Facilities | ₹ | 3,77,73,000.00 | 3,77,73,000.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/fdc2a897-9b2c-448a-8a23-0fdf3b2e85aa.pdf | 37773000 | Match
| 2 | Cost incurred against the estimated cost | ₹ | 1,77,96,751.00 | 2,02,03,960.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/fdc2a897-9b2c-448a-8a23-0fdf3b2e85aa.pdf | 20893600 | Mismatch
| 3 | Work done in Percentage (as Percentage of the estimated Cost) | % | 47.00 | 53.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/fdc2a897-9b2c-448a-8a23-0fdf3b2e85aa.pdf | 53 | Match
| 4 | Balanced Cost to be Incurred (Based on Estimated Cost) | ₹ | 1,99,76,249.00 | 1,75,69,040.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/fdc2a897-9b2c-448a-8a23-0fdf3b2e85aa.pdf | 17569400 | Mismatch
| 5 | Cost Incurred on Additional/Extra Items not included in the Estimated Cost | ₹ | 0.00 | 0.00 | https://reraapp.rajasthan.gov.in//Content/uploads/QPR/R2/fdc2a897-9b2c-448a-8a23-0fdf3b2e85aa.pdf | 0 | Match